## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/04/2025-09/11/2025 | - Selected a project idea - Setup the GitHub repo - Put the basic skeleton together as a proof of concept | Team members have different skill sets. some don't have experience with the React | One person dropped the class | We will start using Jira starting the itteration 1 |  | N/A | N/A | N/A | N/A | 77 | 69 | 2 | 20 | 9 | 6 | 15 | 10 | 10 | 2 | N/A
1 | 09/12/2025-09/23/2025 | - Setup a project in Jira - Setup weekly sprint rview and sprint planning meetings - Define user stories in Jira board and define subtasks for each story - Assign tasks to team members - Develop new features, setup Docker, setup DB, improve the UI. | No issue | No issue | Started using Jira, and setup weekly meetings | 31 | 36 | 9 | 8 | 1 | 181 | 166 | 9 | 49 | 11 | 8 | 51 | 31 | 25 | 18 | N/A
2 | 09/24/2025-10/07/2025 | - Completed sprints in Jira and started new sprints - Defined user stories and related tasks and assigned tasks to the team members - Develop new features for the App - Write unit tests for the code - Improve the CI/CD pipe line - Bug fixes in the code and in the automation in github | No issue | No issue | Use Jira, create user stories in weekly sprint planning meetings and assign tasks to everyone | 57 | 69 | 15 | 12 | 3 | 182 | 163 | 9 | 50 | 7 | 6 | 48 | 28 | 19 | 30 | N/A
3 | 10/8/2025-10/14/2025 | - Completed sprints in Jira and started new sprints - Reviewed the remaining user stories and bugs - Develop new features for the App - Write unit tests for the code - Improve the CI/CD pipe line - Bug fixes in the code | No issue | No issue | Use Jira, create user stories in weekly sprint planning meetings and assign tasks to everyone | 38 | 46 | 14 | 18 | 4 | 207 | 188 | 12 | 45 | 3 | 23 | 44 | 24 | 21 | 28 | N/A

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Robin Roeoesli | Wrote the Management Plan, Risk Management, and Timeline sections of SPPP; contributed updates after feedback in later iterations. | Defined user stories, epics, and acceptance criteria in Jira; refined scope and added estimates; reworked requirements for UI harmonization in Iteration 2. | Designed sidebar and global theme layouts using Material UI; created an alternative logo that matches the new design, typography, and color palette for consistent branding. | Created and updated manual test documentation; participated in Lab 3 with Jest test example; verified UI and backend functionality manually after major changes. | Co-led Iteration 2 and final presentation preparation with Deasy; built presentation slides for the frontend, wa repsonible for the demo, recorded it and managed visual consistency and demo flow. | Implemented responsive sidebar, groq AI functionality, integrated Material UI throughout the app, added routing between /community and /ai, fixed identifier bugs, and refactored UI components for consistency. | Conducted manual UI testing in browser; verified DB interaction using DBeaver; used Playwright selectors for test preparation; contributed to Jest test setup in Lab 3. | Configured .env file and my local PostgreSQL connection; ensured backend and frontend containers ran correctly. | Set up Jira project, prepared meeting minutes, handled documentation updates, communicated with team on priorities, and discussed issues with professor regarding configuration. | Used ChatGPT and Copilot to support coding, testing, and documentation; steadily improved understanding of Material UI, Socket.IO, and NestJS; strong engagement in management and coordination activities.
Masih Vahida | - Complete the "Overview" and "Related Work" sections - Address the comments and questions - AI Section | Define user stories and acceptance criteria | -Review and address the comments | - Review only | - Create presentation for iteration 0 - Create demo video for iteration 0 - Contribute to presentation for iteration 3 - Contribute to demo video for iteration 3 | - Add the team members to the repo as colaborators - Setup rules - Implement the base Chat UI skeleton, the chat container with autoscroll feature, Text input box, - Implement the Socket.io emits and handlers for sending and receiving messages - Implement the "User is Typing" feature - Implement the shift+enter feature to go to the next line - Implement the send-on-enter feature - Develop Unit tests and run manual and automated tests - Code reviews and PR approvals | - Wrote and ran unit tests for the features i added tothe code. - Ran manual functional tests to test the entire app, both backend and frontend. | Test and review, make sure the app is functional. | - Wrote meeting minutes - Setup regular meetings - Sprint review and sprint planning sessions - Review, create, and assign user stories. | - Used ChatGPT and Gemni for coding, learning and getting recommendations - Familiarize myself with JavaScript and React. - Learn Docker, create docker file, create image
Deasia Little | - Authored the initial Quality Assurance Plan, outlining the testing strategy, tools, metrics, and standards to be followed throughout the project. - Updated the CI/CD Pipeline section after Iteration 3 to reflect the finalized implementation, including detailed descriptions of the Docker-based build process, service readiness checks, Playwright test execution, and GitHub Actions workflow. | - Defined detailed user stories, subtasks, and acceptance criteria for all three sprint planning meetings (Iterations 1, 2, and 3). - Estimated story points for tickets assigned to myself, helping the team manage velocity and plan sprints effectively. | - Review only | - Created the initial Software Test Document (STD), establishing the structure for documenting all testing activities throughout the course. - Iteratively updated the STD for each project iteration, incorporating new test cases, automation updates, test result summaries, and CI/CD test outcomes. - Linked all related external testing artifacts (e.g., screenshots, HTML reports, metrics outputs, and manual test plans) from GitHub to ensure traceability and accessibility. - Ensured the STD aligned with feedback, included edge case test coverage, and reflected the evolving scope of features and defects. | - Co-contributed to the Iteration 2 presentation alongside Robin. - Created and designed the backend and testing slides for Iteration 2. - Recorded the video presentation for Iteration 2’s submission. - Created the testing slides for the Iteration 3 submission. - Recorded the video presentation for the testing portion of Iteration 3. | - Reviewed and approved pull requests across multiple iterations. - Configured the codebase to support Playwright test execution. - Added 116 automated end-to-end tests using Playwright. - Developed 3 custom QA metrics scripts to calculate: Lines of Code (LOC), Number of functions, Cyclomatic complexity - Integrated the QA metrics scripts into the CI pipeline for automated reporting. - Configured the CI pipeline to run Playwright tests and generate GitHub issues for failed tests. - Created a custom script to transform raw Playwright JSON results into a readable Markdown summary. - Integrated the readable test summary script into the CI pipeline for auto-generation. | - Created the initial Software Test Description (STD) document and maintained it throughout all three iterations. - Authored and structured both manual and automated test sections, ensuring clear traceability from user stories to tests. - Defined test objectives, scope, feature-to-test mapping, and defect management processes. - Developed and integrated 116 automated Playwright tests, covering all key features including login, registration, chat, sidebar interactions, and help dialogs. - Implemented edge case manual tests, targeting both “happy path” and “unhappy path” scenarios (e.g., invalid login attempts, registration errors). - Wrote a custom GitHub Actions workflow to run Playwright tests, generate test summaries, and auto-create GitHub issues for failed tests. - Created a Node.js script to convert JSON test results into a readable Markdown report for easier grading and debugging. - Organized and linked external testing artifacts (screenshots, HTML reports, metrics output, test cases spreadsheet) from GitHub into the STD for full transparency. - Contributed testing-related slides and delivered the video presentation segment covering QA and CI/CD for Iteration 3. - In Iteration 3, refactored 60+ existing Playwright tests to align with the updated Material UI component structure, which initially lacked data-testid attributes. | - Created the GitHub Actions CI/CD pipeline to automate: Database seeding, Execution of Playwright test suite, Metrics script execution (LOC, function count, cyclomatic complexity), and Artifact and report uploads. - Integrated Playwright, Node scripts, and reporting steps into the CI flow. - Implemented a conditional job to generate GitHub issues automatically on test failures using test output artifacts. - Configured workflows to generate and upload artifacts (e.g., results.json, screenshots, HTML reports) for debugging - Linked all CI artifacts to the STD and SPP for reproducibility and documentation. | - Actively participated in team Discord discussions, providing updates, feedback, and support throughout the semester. - Hosted and led the group meeting during one of the sprint planning weeks, guiding discussion and ensuring task assignments were clear. - Reviewed and approved multiple GitHub pull requests, providing constructive feedback and ensuring alignment with project goals. - Collaborated cross-functionally to resolve blockers, coordinate deadlines, and help the team stay on track during all three iterations. | Used ChatGPT to draft test plans, refactor code, troubleshoot CI issues, and summarize reports, which helped save time and improve quality.
Jordyn Lipsey | -Wrote the Configuration Management Plan sections of SPPP (including Tools, code commit guideline and git branching strategy, and CI/CD plan). -Wrote code review process and defect management sections of Quality Assurance Plan section of SPPP. Contributed to updates regarding feedback from professor | - Defined user stories, subtasks, acceptance criteria, and estimated story points for sprint planning meeting | -Wrote introduction only | -Review only on STD Document | -Created and recorded presentation for iteration 0 (inlcuding slides and video for meeting the team, project proposal, and techstack) -Created and recorded presentation for iteration 1 (including presentation on frontend and backend components, database design, security deisgn, and socket.io) -Created and recorded presentation for iteration 3 (including introduction and security slides and video) | -Designed login and register screen to securely enter user name and password -Implemented JWT authentication and passport-local strategy to authenticate and register accounts -Created profile tab on sidebar to update display name, theme, and avatar for a user -Integrated with authentication system to ensure only users can modify their own profile | - Performed manual UI testing in browser when implementing UI and authentication features. Created several error responses for edge cases - Contributed to Jest test setup in Lab 3 for user login and registration | - Set up Docker for frontend and backend, and docker-compose for entire application. Implemented secrets management in Docker - Leveraged GitHub Actions to kick off code scanning (ESLinting) - Leveraged GitHub Actions to run the integration tests using Playwright - Leveraged GitHub Actions to perfrom security checks (dependency vulnerability scan, static code analysis, and container vulnerability scans) - Leveraged GitHub Actions to build and push our docker image to GHCR | - Participated in weekly team meetings - Participated in team Discord discussions - Collaborated with other team member individually when needed (integration of the DB with authentication system, integration of testing into CI/CD pipelines, and collaborating with other team member during presentation planning) - Responsive with pull requests and reviews, and tackled bugs in a timely manner - Participated in sprint planning by creating Jira stories and documenting stories completed | Used ChatGPT to draft docker files and authentication setup, debug CI/CD pipeline issues, and help with writing cleanup on reports and presentations
Ardit Briskaj | - Wrote the proposed high level requirements including both functional requirements and non functional requirements | Defined user stories for some of the main app features and created appropriate sub tasks for them. Estimated stories during scrum calls and added story descriptions. | - Wrote all of SDD files and created the different diagrams in SDD document. I did not write the introduction file. | - Reviewed only | - Did the demo section of the app of iteration 1. - Did several slides demo on iteration 3. - Created a few of the diagrams that were part of iteration presentaiton slides | - Set up the foundation of UI and API skeletons for the project - Integrated Socket.io for real-time communication between UI and API - Configured a PostgreSQL database hosted in AWS RDS. - Connected the database to the API using TypeORM. - Implemented repository logic to store and retrieve user messages and accounts. - Added message rection feature using Material UI - Resolved a few app-breaking issues throughout the project. - Wrote a few unit tests for api side mainly on socket io event functions - Reviewed a few PRs throughout the project. | - Wrote a few unit tests for api side mainly on socket io event functions - Mainly performed manual testing often to check the project was runable after the first iteration. - Pointed out several times a few issue with the project and volunteered to fix them after catching them while doing manual testing. | - I set up the skeleton UI and API to initially kick off the project, pushed them to our repo and created initial READ me files to help the other team members get set up with the project locally. I did not focus much on this section after the first 2 weeks. | - Participated in all but one of the team weekly meetings - Lead one the meetings and took charge of creating and refining stories - Constantly announced bugs and issues and things we had to work on on the discord channel - Reach out to team members individually a few times when we were wrapping up items due for some iterations - Communicated out to the team both during iteration 1 and 3 which I helped with sumission and the demos due for both and alterted them with the status of the submission as I worked through it | - Used Copilot a few times to help me kick off the initial file structure, mainly on setting up teh db config module file and the first repository file so I could get familiar with the syntax

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Masih
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Masih Vahida, Team Leader, Design and implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/09 | 25 | 24 | 1 | 0 - review the course material, learn typescripts and react, get myself familiarize with the tools 1 - Define high level requirements, and a product overview 2 - make project plan, communicate with team members to proceed 3 - Implement basic structure for sending and receiving messages in the front end, modify the backend code accordingly to communicate with teh front end 4 - Run tests using local server and also AWS server to test the basic functionalites of the App 5 - Communicate with team members, setup meetings | 6 | 2 | 1 | 8 | 4 | 3 | 0 | 0 | Chat GPT, Use to get recommendation on how to add buttons and text input box to the GUI in react Use to get recommendation on the User Interface features Use to get recommendation on how to setup the tools and make the basic app running on local server Use to get recommendation on how to setup proper node version on the Ubuntu shell in windows Use to get recommendation on how to run both the front end and back end on the remote server It was very usefull. i tried different methods suggested by AI and chose the best and modified the code to make it the way i wanted it. | 1. Write 3 sections of SPPP 2. Set up git, commit, push to github per lab1 instruction, code review, branch merges to main 3. Participate in Iteration 0 presentation 4. Coding for both backend and front end | 1. not familiar with React and TypeScript. had to watch tutorials and learn | Setup a standup meeting, define tasks for everyone and continue development | 0 - Continue communication with team members 1 - Participate in meetings 3 - Review the requirements 4 - Continue contributing to the code development | 15
2 | 09/10-09/16 | 20 | 19 | 1 | 0 - review the course material, learn more about class diagrams and docker 1 - Implement new features discussed on sprint planning and the tasks assigned to me 2 - Manually tested the new features added to the code. 3 - Communicate with team members, setup meetings | 7 | 0 | 0 | 7 | 2 | 3 | 0 | 0 | Chat GPT, Gemni Use to get recommendation on how to add timeout timer for the user typing indicator Use to get recommendation on the auto scroll feature Use to get recommendation on how to setup and run docker It was very usefull. i tried different methods suggested by AI and chose the best and modified the code to make it the way i wanted it. | 1. Write 3 sections of SPPP 2. Set up git, commit, push to github per lab1 instruction, code review, branch merges to main 3. Participate in Iteration 0 presentation 4. Coding for both backend and front end | 1. not familiar with Docker and Software class diagrams | Continue with the standup meetings, define new user stories, new tasks and collaborate with the team to add new features to the app | 0 - Continue communication with team members 1 - Participate in meetings 2 - Create and review nea user stories and tasks 3 - Continue contributing to the code development 4 - Continue going over the course materials, learn new stuff | 15
3 | 09/17-09/23 | 18 | 17 | 1 | 0 - review the course material, learn more about micro services, and different architectures 1 - Implement new features discussed on sprint planning and the tasks assigned to me 2 - Manually tested the new features added to the code. 3 - Communicate with team members, setup meetings | 9 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | Chat GPT, Gemni Use to get recommendation on how to add timeout timer for the user typing indicator Use to get recommendation on the auto scroll feature Use to get recommendation on how to setup and run docker It was very usefull. i tried different methods suggested by AI and chose the best and modified the code to make it the way i wanted it. | 1. Write 3 sections of SPPP 2. Set up git, commit, push to github per lab1 instruction, code review, branch merges to main 3. Participate in Iteration 0 presentation 4. Coding for both backend and front end | 1. not familiar with Docker and Software class diagrams | Continue with the standup meetings, define new user stories, new tasks and collaborate with the team to add new features to the app | 0 - Continue communication with team members 1 - Participate in meetings 2 - Create and review nea user stories and tasks 3 - Continue contributing to the code development 4 - Continue going over the course materials, learn new stuff | 15
4 | 09/24-09/30 | 22 | 21 | 1 | 0 - review the course material, study micro services, leatned about writing unit tests and tools to use for that 1 - Implement new features discussed on sprint planning and the tasks assigned to me 2 - Wrote unit tests for the new features added to the code. 3 - Communicate with team members, setup meetings | 10 | 0 | 0 | 5 | 3 | 3 | 0 | 0 | Chat GPT, Gemni Use to get recommendations on how to setup tools for unit test Use to get recommendation on how to write test code Use to get recommendation on how to run tests It was very usefull. directed me on the things needed to learn for testing and showed me ecamples on how to write unit test code | 1. Coding for both backend and front end 2. Developing unit tests 3. implementing new features to the code 4. participating weekly meetings and sprint planning | 1. Not familiar with unit tests and how to write and run it | Continue with the standup meetings, define new user stories, new tasks and collaborate with the team to add new features to the app | 0 - Continue communication with team members 1 - Participate in meetings 2 - Create and review new user stories and tasks 3 - Continue contributing to the code development 4 - Continue going over the course materials, learn new stuff | 15
5 | 10/01-10/07 | 17 | 16 | 1 | 0 - review the course material, study micro services, leatned about writing unit tests and tools to use for that 1 - Implement new features discussed on sprint planning and the tasks assigned to me 2 - Wrote unit tests for the new features added to the code. 3 - Communicate with team members, setup meetings | 7 | 0 | 0 | 4 | 2 | 3 | 0 | 0 | Chat GPT, Gemni Use to get recommendations on how to add help dialog to the gui Use to get recommendation on how to write test code It was very usefull. directed me with the changes needed to the code and writing test code for it | 1. Coding for front end 2. Developing unit tests 3. implementing new features to the code 4. participating weekly meetings and sprint planning | 1. Not familiar with javascript fopr GUI design very well | Continue with the standup meetings, define new user stories, new tasks and collaborate with the team to add new features to the app | 0 - Continue communication with team members 1 - Participate in meetings 2 - Create and review new user stories and tasks 3 - Continue contributing to the code development 4 - Continue going over the course materials, learn new stuff | 15
6 | 10/08-10/14 | 16 | 15 | 1 | 0 - review the course material, study diagrams. 1 - Implement new features discussed on sprint planning and the tasks assigned to me 2 - Communicate with team members, setup meetings 3 - Test the final code's functionality locally 4 - Create presentation and demo video | 8 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | Chat GPT, Gemni Use to get recommendations on how to add help dialog to the gui Use to get recommendation on how to write test code It was very usefull. directed me with the changes needed to the code and writing test code for it | 1. Coding for front end 2. Developing unit tests 3. implementing new features to the code 4. participating weekly meetings and sprint planning | 1. Not familiar with javascript fopr GUI design very well | Continue with the standup meetings, define new user stories, new tasks and collaborate with the team to add new features to the app | 0 - Continue communication with team members 1 - Participate in meetings 2 - Create and review new user stories and tasks 3 - Continue contributing to the code development 4 - Continue going over the course materials, learn new stuff | 15

## Ardit
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Ardit Briskaj, Design and Implementation Leader, Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/09 | 15 | 14 | 1 | 0 - Learn how to set up a streamlit project, learn how to set up a react project 1 - Define high level requirements on SPPP document 2 - Asked copilot to give us some visual mock ups of what our app could look like and the application logo. Integrated it with the UI skeleton. Coordinated with team to choose and plan out our tech stacks and how to connect all the project pieces 3 - Set up both UI and API skeleton for our project. Initially set up a Streamlit UI but switch to React because it didnt fit our needs. Also set up a NestJs project for our back end. Integrated socket.io client with UI skeleton and server for back end 4 - Manually tested UI and API after setting up the skeletons 5 - Reached out to team for PR reviews and get feedback on which techstacks to use while setting up skeletons. 7 - Wrote README.md files on how to set up the project locally and run it. | 2 | 2 | 2 | 5 | 1 | 1 | 0 | 1 | I used copilot twice, once to set give me a logo for our Chit Chat Application. The second time was to give me a visual representation of what our application can look like.. I did use the results for both times and it was very helpful as I am not very creative when it comes to UX. | 1. Wrote the functional requirements section of SPP 2. Set up a working UI in Vite+React and API in NestJS skeleton and integrated them with socket.io. 3. Created README.md files so the other team members can follow it and set up the project locally. | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. We initially went with streamlit but found it hard to integrate it with socket.io because of the lack of observability in python. Sockets are actively listening to new messages and render changes in real time, streamlit was not allowing us to easily do that. | 0 - Create the main user interface in UI with all the components needed and also set up all the socket listners needed for the entire application. Test it with multiple users. 1 - Lead the next team meeting and track meeting minutes 2 - Be part of the next demo | 15
2 | 09/09-09/16 | 21 | 20 | 1 | 0 - Learnt how to set up a postgres database and host is in AWS. Learnt how to create tables and properly set column constraints. 1 - Lead the second meeting of the team and took charge of meeting minutes 2 - Designed the applications database schemas and tables and all columns for each table along with column constrains 3 - Created a PostgreSQL databse and set up the 3 main tables with the columns defined from user story. Set up an aws server and hosted the database. Configured the aws VPC to allow connectes from pgAdmin and application 4 - Manually tested the database and aws server. 5 - Lead the second meeting and took minute meeting notes. Lead the first backlog and sprint planning and created stories as we decided as a team if we needed new ones. Constantly communicated with team through Discord 6 - All configrations related to setting up aws server | 3 | 2 | 1 | 8 | 1 | 5 | 0 | 0 | I only used chatgpt to ask it questions on how to navgiate aws console and how to configure the VPC of the server to allow outside connections. | 1. Set up database 2. Created db schema and populated db tables and columns. 3. Set up and configured aws server to host postgresql db | 1. Not familiar with aws before so it took a little learning knowing where to find what and how to configure the db and allow connection from outside aws. |  | 1. Create db controller in the back end so ui can interact with server and server can perform db actions. We have a story to create login ui so this sprint is the perfect timing to have the server connected to db. | 20
3 | 09/16-09/23 | 25 | 24 | 1 | 0 - Learnt how to connect a database with a nestjs back end server via typeorm 1 - Filled out the SDD documentation with all the application architecture designs and patterns 3- Implemented the database controller for back end to connect to our database ( still work in progress wrapping up story, not merged yet) 4 - Manually tested the connection between the database and the application and saving and inserting data from nestJs to postgreSQL 5 - Coordinated with Jordyn to plan out the iteration 1 release items, did the demo for iteration 1, and filled out the SDD document required for iteration 1 | 5 | 5 | 0 | 10 | 2 | 2 | 0 | 0 | I did not used any AI tools for this sprint. I was more focused on finishing up my db connection story to the application and the demo and preparation for iteration 1 submission. | 1. Worked on connecting the database with our application 2. Filled out SDD document about design and software patterns and created the application class diagrams 3. Did the demo for iteration 1 showcase the application progress to date and a quick db demo | 1. Item crunch due to long work hours and the due date for iteration 1 coming up |  | 1. I want to be more involved with more UI work so I will focus on application UI enhancements 2. Will start focusing on writing unit tests | 15
4 | 09/24-09/30 | 20 | 19 | 1 | 0 - Learnt how to write and mock objects for jest. 3- Finalized the changes that implemented the databse controller and connection between the app and database. Messages sent and rcieved are now saved in database and retrieved when user logs back in 4 - Manually tested the changes related to saving messages and retrieving them when user logs in also wrote a few jest test for backend. 5 - I kept communicating with team via discord as I was not available to attend the meeting this sunday. | 3 | 0 | 0 | 12 | 2 | 2 | 0 | 0 | Used AI to help me configure the initial typeorm configuration and set up the first entity file so I could use as a base for the other entity objects | 1. Finalized the typeorm changes and now users' messages are saved and retrived when they log back in | 1. AWS RDS was set up on a weekly password rotation which caused our password to expire the day of grading, creating confusing and caused the app to not run. |  | 1. I will work on reaction system on messages end to end, finish the ui work, api and any changes needed on db side. | 20
5 | 10/01-10/07 | 25 | 24 | 1 | 0 - Learnt how to use material UI for react 3- Implemented the reaction system for messages and also integrated it with db to save reactions on db 4 - Manually tested the changes related to reacting to messages 5 - Communicated with team via discord about all findings and attended sunday meeting where we discussed remaining items for last iteration. | 5 | 0 | 0 | 15 | 2 | 2 | 0 | 0 | Used AI to help me with some of the styling for reaction hover tooltip | 1. Finished one of our app's features the ability to react to messages and see the reactions of others. | Not enough time to learn material UI within one week, used ai to help me quickly get started using and integrating it within our application |  | Will wrap up the last story for the application which is a message notification system, also will jump in if any help is needed to finalize the application. | 15
6 | 10/07-10/14 | 9 | 8 | 1 | 4 - tested the application to make sure its runnable and fixed some issues throughout the week that made the application unrunable for some time 5 - Work on puttin together the teams presentaion and iteration 3 submission | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | Did not use AI this week, this was more wrapping up final project and focusing on bugs and wrapping up final iteration presentation | 1. Pushed 2 PRs that fixed 2 issue cuasing the project not run, also worked on putting everyone's presentation videos together and getting them ready for iteration 3 submission | A little hard to focus on adding features on project on the last week with final around the corner and having to study for it and also getting ready for end of class submissions.

## Jordyn
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Jordyn Lipsey, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/09 | 10 | 9 | 1 | 0 - Reviewed the course material, researched GitHub, setup Team 1 folder 1 - Define configuration requirements, code revew process, and defect management 5 - Communicate with team members, took meeting minutes, created and recored presentation for project proposal 6 - Set up GitHub labels | 4 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | Chat GPT: Used to make logo of app | 1. Wrote 5 sections of SPPP (Configuration Management Plan (Tools, Code Commit Guideline and Git Branching Strategy) and Quality Assurance Plan (Code Review Process, Defect Management) 2. Copied the repo, updated the read.me, commited, pushed to GitHub for Lab 1 3. Participate in Iteration 0 presentation (made presentation and recorded video) | 1. Difficulty setting up GitHub. If you have multiple GiHub accounts, there will be access issues. Once I researched the situation, I recopied the repo to another device to avoid setting up account management | Issue resolved | - Look into Docker, Podman, and Passport.js - Review PRs more closely and ensure standards - Contribute to the App | 15
2 | 09/09-09/16 | 26 | 25 | 1 | 0 - Learnt how to set up a dockerfile for our application, including Dockerfile, dockerignore, and Docker-compose. Learnt how to set up CI/CD pipelines using GitHubs Actions. 1 - Create Docker documentation for the team, created several stories and documented completion 4 - Set up GitHub Action to run E2E testing, code scanning (linting), and build and push docker image on merge to main branch. 5 - Communicated constantly with team members through Discord (including working with team members to use their integration test in CI/CD pipelines), created and recored presentation for iteration 1 project 6 - Set up Docker for our project | 4 | 1 | 0 | 0 | 8 | 3 | 9 | 0 | ChatGPT: Used ChatGPT to debug Podman interferance issue with Dockerfile | 1. Set up Docker for our project. Including Dockerfile and dockerignore for frontend and backend, and docker-compose for entire application 2. Set up start of CI/CD pipelines for our project. Leveraged GitHub Actions to kick off code scanning, integration tests, and build and push our docker image to GHCR. 3. Participate in Iteration 1 presentation (made presentation and recorded video) | 1. Using Docker was new to me - there was a large learning curve with installing docker and creating our Dockerfile. I had a lingering Podman running in the backround, that took lots of debugging to figure out what was causing issues with the Dockerfile I was trying to setup. 2. Initially tried to create development and production Dockerfile, which had access issue to certain packages. | 1. Issue Resolved - uninstalled Podman from my desktop 2. Issue Resolved - using only development Dockerfile | -Finish CI/CD pipelines (stage, aq, and prod environments for releases) -Implement account sign in using PassportJS | 20
3 | 9/16-9/23 | 20 | 19 | 1 | 0 - I spent time this week reviewing the course material and watching zoom lecture. 4 - Debugged GitHub Action to run E2E testing, code scanning (linting), and build and push docker image on merge to main branch after merging changing broke pipelines 5 - Communicated constantly with team members through Discord (including working with team members to use their integration test in CI/CD pipelines) 6 - Spent time debugging and modifying our Docker files and CI/CD pipelines (Git Hub Actions) | 3 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | ChatGPT: Used ChatGPT to debug issues with GitHub Actions | 1. Fixed bugs on docker and CI/CD pipelines | This week the biggest challenege was working on the issues with the docker files and CI/CD pipelines that were introduced with PRs. The solution wasn't straight forward. | I worked with the QA leader to get the CI pipeline in a good state. There were a lot of bugs introduced, so working through these took up a lot of time | Next week I plan to implement authentication and work with the team on any additional CI/CD pipeline work that needs to be done. | 20
4 | 9/23-9/30 | 22 | 21 | 1 | 0 - Learnt how to set up Passport for our application, including login screen for the UI. I spent time this week reviewing the course material and watching zoom lecture. 5 - Communicated constantly with team members through Discord and attended weekly planning meeting 6 - Designed login screen to securely enter username and password, register user, implemented passport strategy to authenticate accounts 7 - Spent time working on the Lab 3 (created login test to test registering a user, find account by username, and throw an error if the user exists) and Quiz 3 assignment. | 3 | 0 | 0 | 0 | 0 | 2 | 12 | 4 | ChatGPT: Used ChatGPT to help set up Authentication | 1. Designed login screen to securely enter user name and password 2. Implemented passport-local strategy to authenticate accounts 3. Implemented session handing with token to persist so user remains logged in until the user logs out or the session expires 4. Add error messages like "Invalid credentials" so the user knows why login failed | No Issues | No Issues | Next week I plan to wrap up authentication (some small bugs and improvements could be made) and implement profile picture for the user. | 20
5 | 10/1-10/7 | 21 | 20 | 1 | 0 - I spent time this week reviewing the course material and watching zoom lecture. 2 - Designed profile page for user to customize their user with display name, theme, and avatar 5 - Communicated constantly with team members through Discord and attended weekly planning meeting. | 3 | 0 | 15 | 0 | 0 | 2 | 0 | 0 | ChatGPT: Used ChatGPT to create profile page | 1. Created profile tab on sidebar to update display name, theme, and avatar for a user 2. Integrated with authentication system to ensure only users can modify their own profile 3. Updated authentication system to persist session even when page refreshes 4. Added logout button | This week's biggest challenge was integrating with the authentication system to ensure only a valid user could update their profile customizations. | Issue resolved. | Next week I plan to wrap up all my tasks - make sure authentication works with all the additional features being added to the UI and plan to use the user custimzation in place throughout the UI (profile avatar, theme, display name) | 20
6 | 10/8-10/14 | 21 | 20 | 1 | 0 - I spent time this week reviewing the course material and watching zoom lecture. 5 - Communicated constantly with team members through Discord (including working with QA Leader to debug CI/CD pipelines) and attended weekly plannng meeting. Created and recored portion of presentation for iteraton 3 6 - Created security github action. Debugged C/CD pipeline and docker to work with new environment (considering updates to database, GROQ key, and authentcaton system). | 3 | 0 | 0 | 0 | 0 | 6 | 11 | 0 | I used Chatgpt this week to help debug the Github actions in the CI pipelines and create security GitHub Action. | 1. Added Security Github Action 2. Reconfigured docker and CI/CD pipelines to work with the final app environment. 3. Fixed /Register route bug | Additional refactoring was need on docker and CI/CD pipelines because of the continuously changing app - the addition of GROQ key, database, and authentication system needed to be accounted for, which couldn't be accounted for when docker was initially set up. It was difficult when the container would run locally, and CI/CD pipelines would still fail. | Issue Resolved | Focus on studying for final exam | 0

## Deasia
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Deasia Little, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/2 | 7 | 3 | 1 | 0 - I attended the class lectures and reviewed the group project documents. 5 - I attended the weekly team meeting to discuss project ideas and tech stacks/testing frameworks that we would use to implement our project. 6 - Setup Git, VS Code, and Github Desktop on my computer. | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | I did not use AI tools on this week | 1. Contributed to the projects tech stack/framework discussion 2. Contributed to the project's file team.md | There were no issues this week with setting up my development environment for the class. | I encountered no issues this week. | Next week's tasks include test planning for the first software tickets, setting up the testing framework, and automating tests. | 20
2 | 9/9-9/16 | 10 | 6 | 1 | 0 - Reviewed the course material, attended the class lectures, and learned about Playwright with Javascript 2 - I settled down on a testing framework to be used for the project. Since we decided to use JavaScript, I switch from PyTest to Playwright. I created stories to be implemented for interation 1. The stories included subtasks and acceptance criteria. 4 - I spent time creating use cases to be tested for the project. Also, I created smoke tests in Playwright to get acclimated to the framework. 5 - Time was spent meeting with the team to review assignments for the project. We assigned stories and tasks amongst team members to be completed for the first iteration. | 4 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 1. Used ChatGPT to research testing frameworks compatible with React. This was used to make a decision for automated testing frameworks to be used for the project. 2. Research the benefits of using Playwright vs. Selenium with Javascript. I was unfamilar with Playwright so I did not understand it's native compatibility with React and why it was better than Selenium. This helped my foundational knowledge to get started with testing, | 1. Developed the QA plan for the team's SPP | I am unfamiliar with JavaScript so I will be learning over the course of this project while writing the tests. | I have been researching and practicing using Playwright with JavaScript to be better prepared for when testing starts. | I plan on writing the acceptance tests for iteration 1. I will then proceed to automate the tests. | 20
3 | 9/16-9/23 | 19 | 15 | 1 | 0 - I spent time this week reviewing the course material and attending the class lectures. 3 - This week 4 stories where implemented for our software. I created automated tests in Playwright for all of the completed stories including the guest chat feature, sidebar menu, auto scroll, and typing indicator. There were 23 automated tests total that were implemented. 4 - I executed the automated tests against our main branch included all the features completed in Sprint 1. I also conducted 9 manual tests for our web app's core features. 5 - I attended the weekly group meeting where we conducted sprint planning and group assigments. 6 - I created a QA metrics script that analyzed lines of code, code complexity, and automated test coverage that will be used in our CI pipeline. | 3 | 0 | 0 | 9 | 3 | 1 | 3 | 0 | 1. I used ChatGPT to help with the QA metrics script. This was helpful as I am not familiar with CI pipelines and how metrics are gathered. ChatGPT was useful in helping me find tool to calculate lines of code and code complexity. | 1. This iteration I delivered the project's Playwright setup 2. 23 automated tests for completed stories with test results 3. 9 manual tests for completed stories with test results 4. First draft of STD | I had a lot of trouble with my environment running automated tested in playwright on one branch and executing the QA metrics script on another branch. | The automated test setup is now merged into main so integrate my changes with the branch containing the QA metrics script. | I will continue to automate tests for completed software stories. In addition to that, I will integrate the end to end tests and QA metrics into our CI pipeline so each PR will be run with the tests. | 20
4 | 9/23-9/30 | 16 | 9 |  | 0 - I spent time this week reviewing the lecture material and attending the live classroom sessions. 6 - This week I spent time refining the QA metrics to run in the CI pipeline. Scripts were created to calculate the lines of code, code complexity, and number of functions. The automated Playwright tests were configured to run on pull requests. 5 - I ran the weekly sprint planning meeting anf updated the JIRA board 7 - I spent time working on the Lab 3 and Quiz 3 assignment. | 3 | 0 | 0 | 0 | 0 | 1 | 9 | 3 | 1. I used ChatGPT to help figure out the tools and configurations required to run the QA metrics. This was used to incorporate metrics into the CI pipeline. 2. ChatGPT was used to automatically generate Github Issues based on failed tests on pull requests. This is useful in fully automating our pipeline. | 1. Updated the CI pipeline to run Playwright tests on pull request. 2. Generate scripts to count lines of code, function counts, and code complexity. 3. Incorporated the QA metrics scripts into the CI pipeline. | This week I face a lot of challeneges ensuring the QA metrics and Playwright tests run locally and in the CI pipeline. Because my dev environment is different than the CI pipeline there were errors when running the real CI script that I was unable to uncover until pushing my code. It took a lot of debugging and testing to get the CI pipeline working. | I worked with the configuration leader to get the CI pipeline in a good state. | Next week I plan to continue creating more tests and automating them. This week I spent more time than anticapted with the CI pipeline. | 20
5 | 10/1-10/7 | 20 | 19 | 1 | 6 - This week I spent a lot of time configuring the app to work locally. I had to resolve issues with version mismatches and missing keys. 5 - I spent time attending the weekly group meeting. This week Robin and I are responsible for this iteration's presentation so we spent time on a call discussing our tasking and responsibilited. 4 - This week I created automated tests for core features in iteration 1 and 2. I also added additional details to our test report that includes an easily readable summary of test results for non-developers. 7 - This week along with another team member I am responsible for the iteration 2 presentation and demo that I spent time working on. | 0 | 0 | 0 | 0 | 7 | 1 | 6 | 6 | 1. ChatGpt was used to resolve issues running the app locally. I had various issues with JWT keys and version mismatches that delayed development time. I was able to troubleshoot with ChatGPT's suggestions. 2. I used ChatGPT to help create a script that summarizes test results. As a part of the artifacts generated for the CI pipeline a document included passed/failed results, results per feaure, and cumulative totals of all tests will be generated with each run. This report is useful for an overall view of the stability of our app. | 1. 42 automated test cases were created in Playwright for our core app features. 2. A script was created to parse the playwright.json file into a clear readable summary. 3. I worked on the backend/test portion of the Iteration 2 presentation. 4. Video demo of our Iteration 2 presentation. 5. Generated Github issues based on failed tests. 6. Latest QA metrics and automated test results | This week I faced a lot of issues running the app locally. The project seems to be missing an .env file needed to run APIs in our backend code. This caused me to lose a lot of test development time. Also, on the last day of the sprint a branch was merged into main that included a full overhaul of our UI design using MaterialUI; consequently, causing all 65 Playwright tests to be broken. As a result, the tests had to be commented out of the CI pipeline for now. I think some of the same local build issues are causing issues in the CI pipeline as it hangs waiting for the backend, | I am working with my teammates to provides them with element names to fix the UI to be compatible with the tests again. Another teammate is resolving the build issues for the project. I am hoping that resolves the CI issues. | Next week I plan to manually test the remaining features in the project. The UI issue is a blocker in automating tests at the moment and we are on a tight deadline. The manual tests will be documented well. I do plan on refactoring the current automated tests when the UI is fixed. | 20
6 | 10/8-10/14 | 34 | 33 | 3 | 0 - I spent time this week learning the module 6 material 3 - There was a large amount of time this week refactoring automated tests and creating new tests 4 - I ran the automated tests multiple times to verify the tests were functional after they were refactored due to a UI redesign. I also added and executed new manual test cases. 5 - I attended the weekly group meeting. I collaborated via Google meet with the group's configuration leader to debug the CI issues, 6 - Once the CI pipeline issues were addressed I spent time running the CI pipeline to verify the custom Github actions for database seeding, Playwright tests, report generation, artifacts, and github issue creation were working. | 3 | 0 | 0 | 13 | 4 | 3 | 4 | 7 | I used Chatgpt this week to help debug the Github actions in the CI pipelines. AI was useful in adding logging to the pipeline to resolve build issues, installing packages for scripts, and adding the correct paths for running the actions. | 1. 65 refactored Playwright automated tests 2. Integration of the Playwright tests in the pipeline 3. Iteration 3 testing slides and demo 4. Addition of the STD documents in the Github repo 5. 50 new Playwright automated tests 6. 10 new manual test cases | - I had to refactor over 65 automated Playwright tests due to the UI overhaul to Material UI, which initially lacked stable data-testid selectors. This significantly delayed test stabilization. - I had to integrate the Playwright tests, artifacts, and automated GitHub issue creation into the CI pipeline just two days before the final submission, because the Docker-based CI environment wasn’t fully operational until then. | I worked extended hours during the final week to ensure my tests, reports, and CI integration were completed and functioning despite the last-minute challenges. | This week I plan to focus solely on studying for the final exam for the class. | 20

## Robin
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Robin Roeoesli, Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/2-9/9 | 17 | 16 | 1 | 0 – Reviewed course material, refreshed React basics, and explored example projects online to understand different approaches to chat interfaces. 1 – Participated in initial discussions on project scope, and clarified high-level requirements in Jira. 2 – Sketched out possible interface ideas for me after reviewing other projects online. 3 – Set up the project locally and verified the skeleton app runs properly on my machine. 4 – Ran quick tests on the local setup to confirm dependencies and that the frontend/backend connection works. 5 – Coordinated with the team on responsibilities and proposed priority order. 6 – Set up Jira project board, and created test-tasks and categories. | 4 | 3 | 1 | 2 | 3 | 2 | 1 | 0 | No AI this week | 1. Wrote the Management Plan sections of SPPP (Objectives and Priorities, Risk Management, and Timeline) 2. Copied the repo, updated the read.me, commited, pushed to GitHub for Lab 1 3. Set Up Jira for the team | No Issues | No Issues | - Make sure everyone is using Jira - Contribute to the App | 17
2 | 09/09-09/16 | 22 | 21 | 1 | 0 – Studied Node.js, Stream.js, Socket.IO, and Streamlit; watched tutorials and read documentation, with the steepest learning curve in Streamlit. Reviewed differences in React component design vs. Streamlit’s reactive model. 1 – Defined initial tasks in Jira and adjusted project scope, set labels, priorities, and added estimates for new issues. 2 – Evaluated different approaches to building the sidebar (pure HTML/CSS, Chakra UI, Material UI) and documented pros/cons. 3 – Implemented a fully responsive sidebar using Material UI, integrated it with React Router DOM, and wrapped the App in a reusable layout component. 4 – Tested sidebar across different screen sizes and browsers. 5 – Wrote a detailed PR description, reviewed another team member’s PR, and discussed improvements in Discord. 6 – Set up Jira filters and boards to help the team track tasks efficiently. | 6 | 2 | 2 | 7 | 1 | 3 | 0 | 0 | Used ChatGPT for: - Finding the best way to implement a responsive sidebar in React. - Understanding the sx prop in Material UI. - Drafting a professional GitHub PR description in Markdown format. | - Split frontend into two separate routes (/community and /ai). - Created a reusable Sidebar component. - Updated App.tsx to wrap children with the Sidebar layout. - Integrated React Router DOM for routing. - Added Material UI for styling and UI consistency. - Reviewed teammate’s PR and provided feedback. | Not familiar with Material UI. Required extra time to understand its props and styling system. | Resolved: learned key Material UI patterns (sx, Grid, Box). Decided to migrate existing components to Material UI for consistency. | - Add AI logic to /ai route and connect to backend AI API. - Replace remaining custom styles with Material UI components. - Participate in code reviews and refine routing strategy. | 20
3 | 09/16-09/23 |  |  |  | 0 – Studied Material UI in more depth, experimented with theming, and learned GitHub Desktop workflow. 2 – Designed a new chat interface layout in Material UI, experimented with a consistent theme and typography. 3 – Began implementing the redesigned chat interface and started migrating from CSS to Material UI components. 4 – Tested different Material UI components locally to evaluate styling consistency and responsiveness. 5 – Communicated with team members, participated in online meetings, and discussed design standardization. 6 – Created new Jira tasks and refined backlog for upcoming sprint. | 5 | 1 | 3 | 6 | 1 | 2 | 1 | 0 | - Used GitHub Copilot to suggest Material UI code snippets and help replace custom CSS with components. - Used Copilot for socket-related code examples. - AI was helpful in speeding up UI migration and providing ready-to-use snippets. | - Updated SPPP document. - Updated Risk Management document. - Contributed to progress report updates. - Worked on presentation preparation. - Designed and partially implemented the new Material UI chat interface. | Unsure whether to set up a global Material UI theme or keep styling localized (color palette and typography choices). | Still under review; plan to test both approaches next week before finalizing. | - Finalize Material UI theme harmonization. - Complete AI logic integration on /ai route. - Continue migrating styles fully to Material UI. | 18
4 | 9/23-9/30 | 20 | 18 | 2 | 0 – Reviewed lecture material and live classes; studied NestJS backend concepts; practiced testing exercises online. 1 – Analyzed the new Jira feature for UI harmonization. 2 – Reviewed UI harmonization design requirements from Jira. 3 – Finalized LLM request; reviewed code to understand backend and frontend integration. 4 – Worked on Lab 3 test examples and Quiz 2. 5 – Communicated with team during lab and sprint work. | 6 | 1 | 3 | 2 | 6 | 2 | 0 | 0 | - Used ChatGPT to clarify Jest testing setup, NestJS backend concepts, and UI harmonization approaches; results were helpful and applied directly in code and lab tasks. | - Updated Risk Management document. | all clear | - | - Work on combining the LLM requests and harmonizing the design as well as doing the presentation for the next iteration | 20
5 | 10/01-10/07 | 24 | 21 | 3 | 0 – Studied Material UI customization, Playwright selectors, and reviewed lecture/live-class content; 1 – Reworked and clarified requirements in Jira for UI harmonization; 2 – Designed global theme (colors/typography), refined logo alignment and layout guidelines; 3 – Updated Material UI code, implemented global theme and font across components, integrated new logo, fixed a UI bug, partial refactor from custom CSS; 4 – Manually tested visual changes and basic flows; 5 – Prepared meeting minutes, communicated Iteration 2 hand-in, gave feedback on teammates’ PRs, updated risk management doc; Coordinated seperately with Deasy 6 – Used DBeaver to inspect backend DB and data saving behavior | 5 | 2 | 5 | 6 | 2 | 3 | 1 | 0 | Used ChatGPT and GitHub Copilot to: draft Material UI theme overrides and clarify Playwright selector strategies. | Updated Material UI across screens, introduced global theme + font, added new logo asset, refined Jira requirements, updated risk management document, created meeting minutes, analyzed DB with DBeaver, fixed one UI bug. | Open questions on whether all components should use global theme vs local overrides; minor Playwright selector flakiness on dynamic elements; occasional DB connection hiccups in DBeaver. | Document decision: prefer global theme with component-level overrides only when needed; add data-testid hooks and stabilize selectors; verify DB connection profile and credentials; continue migrating remaining CSS to MUI. | Complete UI harmonization (migrate remaining components to MUI), implement AI logic for /ai route, add an end-to-end test for typing indicator, set up basic Playwright run in CI, prepare PR and code review. | 23
6 | 10/08 - 10/13 | 22 | 19 | 3 | 0 – Reviewed professor feedback and final presentation guidelines, prepared for the final exam, and revisited course materials for clarification; 1 – Reviewed iteration 2 feedback and documented required changes for final iteration; 2 – Created final presentation slides with Deasy, refined design flow and visual consistency; 3 – Fixed identifier bug after Material UI integration, improved minor UI logic, adjusted component layout; 4 – Manually tested bug fixes and ensured visual consistency across pages; 5 – Coordinated with team on final presentation content, communicated .env configuration issue to professor, updated documentation sections; 6 – Tested .env configuration locally using DBeaver and ensured connection stability. | 5 | 2 | 2 | 6 | 2 | 3 | 2 | 0 | Used ChatGPT to troubleshoot environment variable loading in Node.js, verify correct Material UI theming approach, and summarize professor feedback into concise presentation points. The responses were helpful and directly applied to improve both code and documentation. | Created and refined iteration 2 presentation, implemented UI consistency improvements, resolved identifier bug, updated documentation, and validated local environment configuration. | Minor inconsistencies with environment variable management and missing selectors in certain Material UI components. | Finalize environment configuration setup, document missing selector fixes, and complete team presentation and demo preparation. | Prepare for final presentation, ensure environment and database configs are working, finish all UI fixes, and complete project submission materials. | 12