## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/04/2025-09/11/2025 | - Selected a project idea - Setup the GitHub repo - Put the basic skeleton together as a proof of concept | Team members have different skill sets. some don't have experience with the React | One person dropped the class | We will start using Jira starting the itteration 1 |  | N/A | N/A | N/A | N/A | 49 | 46 | 2 | 12 | 6 | 3 | 13 | 5 | 6 | 1 | N/A
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Masih
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Masih Vahida, Team Leader, Design and implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/09 | 24 | 23 | 1 | 0 - review the course material, learn typescripts and react, get myself familiarize with the tools 1 - Define high level requirements, and a product overview 2 - make project plan, communicate with team members to proceed 3 - Implement basic structure for sending and receiving messages in the front end, modify the backend code accordingly to communicate with teh front end 4 - Run tests using local server and also AWS server to test the basic functionalites of the App 5 - Communicate with team members, setup meetings | 6 | 2 | 1 | 8 | 4 | 3 | 0 | 0 | Chat GPT, Use to get recommendation on how to add buttons and text input box to the GUI in react Use to get recommendation on the User Interface features Use to get recommendation on how to setup the tools and make the basic app running on local server Use to get recommendation on how to setup proper node version on the Ubuntu shell in windows Use to get recommendation on how to run both the front end and back end on the remote server It was very usefull. i tried different methods suggested by AI and chose the best and modified the code to make it the way i wanted it. | 1. Write 3 sections of SPPP 2. Set up git, commit, push to github per lab1 instruction, code review, branch merges to main 3. Participate in Iteration 0 presentation 4. Coding for both backend and front end | 1. not familiar with React and TypeScript. had to watch tutorials and learn | Setup a standup meeting, define tasks for everyone and continue development | 0 - Continue communication with team members 1 - Participate in meetings 3 - Review the requirements 4 - Continue contributing to the code development | 15

## Ardit
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Ardit Briskaj, Design and Implementation Leader, Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/10 | 15 | 14 | 1 | 0 - Learn how to set up a streamlit project, learn how to set up a react project 1 - Define high level requirements on SPPP document 2 - Asked copilot to give us some visual mock ups of what our app could look like and the application logo. Integrated it with the UI skeleton. Coordinated with team to choose and plan out our tech stacks and how to connect all the project pieces 3 - Set up both UI and API skeleton for our project. Initially set up a Streamlit UI but switch to React because it didnt fit our needs. Also set up a NestJs project for our back end. Integrated socket.io client with UI skeleton and server for back end 4 - Manually tested UI and API after setting up the skeletons 5 - Reached out to team for PR reviews and get feedback on which techstacks to use while setting up skeletons. 7 - Wrote README.md files on how to set up the project locally and run it. | 2 | 2 | 2 | 5 | 1 | 1 | 0 | 1 | I used copilot twice, once to set give me a logo for our Chit Chat Application. The second time was to give me a visual representation of what our application can look like.. I did use the results for both times and it was very helpful as I am not very creative when it comes to UX. | 1. Wrote the functional requirements section of SPP 2. Set up a working UI in Vite+React and API in NestJS skeleton and integrated them with socket.io. 3. Created README.md files so the other team members can follow it and set up the project locally. | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. We initially went with streamlit but found it hard to integrate it with socket.io because of the lack of observability in python. Sockets are actively listening to new messages and render changes in real time, streamlit was not allowing us to easily do that. | 0 - Create the main user interface in UI with all the components needed and also set up all the socket listners needed for the entire application. Test it with multiple users. 1 - Lead the next team meeting and track meeting minutes 2 - Be part of the next demo | 15

## Jordyn
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Jordyn Lipsey, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/02-09/09 | 10 | 9 | 1 | 0 - Reviewed the course material, researched GitHub, setup Team 1 folder 1 - Define configuration requirements, code revew process, and defect management 5 - Communicate with team members, took meeting minutes, created and recored presentation for project proposal 6 - Set up GitHub labels | 4 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | Chat GPT: Used to make logo of app | 1. Wrote 5 sections of SPPP (Configuration Management Plan (Tools, Code Commit Guideline and Git Branching Strategy) and Quality Assurance Plan (Code Review Process, Defect Management) 2. Copied the repo, updated the read.me, commited, pushed to GitHub for Lab 1 3. Participate in Iteration 0 presentation (made presentation and recorded video) | 1. Difficulty setting up GitHub. If you have multiple GiHub accounts, there will be access issues. Once I researched the situation, I recopied the repo to another device to avoid setting up account management | Issue resolved | - Look into Docker, Podman, and Passport.js - Review PRs more closely and ensure standards - Contribute to the App | 15

## Deasia
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Deasia Little, QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week

## Robin
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Robin Roeoesli, Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week